## Project Plan and Gantt
Project Name | Boek
Project Manager | Joey Williamson
Start Date | 2015-09-02
End Date | 2020-12-28
Overall Progress | 50%
Tasks | Responsible | Start | End | Days | Status
Create Workplan | Joey W | 2020-09-02 | 2020-09-03 | 1 | Complete
Requirements Gathering | Joey W | 2020-09-03 | 2020-09-07 | 4 | In process
Mobile UI | Joey W | 2020-09-07 | 2020-09-12 | 5 | In process
Mobile Registration Screen | Joey W | 2020-09-09 | 2020-09-10 | 1 | Complete
Mobile Login Screen | Joey W | 2020-09-11 | 2020-09-13 | 2 | Complete
Mobile Endpoints | Joey W | 2020-09-14 | 2020-09-17 | 3 | Complete
Passenger Screen | Joey W | 2020-09-17 | 2020-09-21 | 4 | Complete
Driver Screen | Joey W | 2020-09-22 | 2020-09-26 | 4 | Complete
Panic Button | Joey W | 2020-09-27 | 2020-09-29 | 2 | Not started
Mobile Endpoint | Joey W | 2020-09-30 | 2020-10-03 | 3 | In process
Book Lodging Screen | Joey W | 2020-10-04 | 2020-10-06 | 2 | Not started
Host Listing Screen | Joey W | 2020-10-07 | 2020-10-10 | 3 | Not started
Mobile Endpoint | Joey W | 2020-10-11 | 2020-10-15 | 4 | Not started
Booking Gigs | Joey W | 2020-10-16 | 2020-10-19 | 3 | Not started
Gigs Sign Up Screen | Joey W | 2020-10-20 | 2020-10-24 | 4 | Not started
Homepage | Joey W | 2020-10-25 | 2020-10-30 | 5 | Not started
Mobile Endpoint | Joey W | 2020-10-31 | 2020-11-10 | 10 | Not started
Add to play store | Joey W | 2020-11-11 | 2020-11-13 | 2 | Not started
Testing | Joey W | 2020-11-14 | 2020-12-27 | 43 | Not started
Project submition |  | 2020-12-27 | 2020-12-28 | 1